## Gantt Chart
Bright Coffee Shop Sales Analysis — Project Gantt Chart (21 Jun - 03 Jul 2026)
Task | Start Date | End Date | Duration (days)
Data flow & architecture diagram | 2026-06-21 | 2026-06-21 | 1
List key insights & calculations | 2026-06-22 | 2026-06-22 | 1
Convert Excel data to CSV & load | 2026-06-23 | 2026-06-23 | 1
Data transformations (time buckets, unit price fix) | 2026-06-24 | 2026-06-25 | 2
Build pivot tables & dashboards | 2026-06-26 | 2026-06-27 | 2
Create charts & graphs | 2026-06-28 | 2026-06-28 | 1
Methodology document | 2026-06-29 | 2026-06-29 | 1
Key insights & presentation deck | 2026-06-30 | 2026-07-01 | 2
Recommendations | 2026-07-02 | 2026-07-02 | 1
Final review & GitHub submission | 2026-07-03 | 2026-07-03 | 1